AI Technical Program Manager — UST

Week 1 · Exercise 2 · Release-Readiness Checklist v1 — Beacon (Kestrel Health Network)

Final consolidated submission for the Kestrel / Beacon exercise. All six parts completed. Submit as UST_AITPM_Week1_Ex2_Workbook_290222.

# Part 1 · Cover block

| Field | Your entry |
| --- | --- |
| Candidate id | 290222 |
| Week | Week 1 · Exercise 2 · Release-Readiness Checklist v1 (Beacon) |
| Domain track used | Healthcare (Kestrel Health Network / Beacon) |
| Did you use your own live project instead of the case? | No — provided Kestrel / Beacon scenario |
| AI tool(s) used | Claude (Sonnet) & Co-pilot |
| Attempt number | 1 |
| Date | Evidence snapshot: 8 December 2026 (case date) |

# Part 2 · Findings Log (M1)

Every weakness in checklist v0.9 that would stop a careful stranger trusting Beacon is ready. Each names the v0.9 item(s), what is wrong, category, criticality, why it matters to the sponsor, where the proof is, and what Checklist v1 must contain instead.

Category: Dimension gap · Ownership · AI control · Stage gate · Evidence · Contradiction. Delete the grey F0 example row before submitting.

| # | v0.9 item(s) | Finding (what is wrong) | Category | Criticality | Why it matters (for the sponsor) | Evidence reference | What v1 must contain instead | Primary parameter |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| F1 | 11; A5 | [Governance] Item 11 “Clinical safety case signed” rests on Corvid’s Hazard log v2; signed by Corvid’s CSO for Corvid Bench, 18 hazards, none for automated replies, mixed-language messages or nurse-queue capacity. CSS-1 requires a Kestrel clinical safety case and hazard log owned and signed by Kestrel’s CSO; a supplier’s log is an input only. Dr. Helen Mathews has not been asked to review it. Owner is Neha Sharma (delivery), not the CSO. | Dimension gap; Ownership | Critical | A system that triages patients is going live with no Kestrel-owned assessment of its actual hazards, breaching CSS-1. | Part B #11; Part C E7, E2; Part A4 (CSS-1); Part A3 | Review-stage Governance row: Kestrel clinical safety case + hazard log covering auto-replies, mixed-language triage and queue capacity, owned/signed by Dr. Helen Mathews; Corvid’s log an input only. | 1 · Dimension gap |
| F2 | None; 1,2,29 | [Business] v0.9 records approval and board comms but states no pilot success metrics (under-triage rate, time-to-triage, nurse-queue load) with baselines and no abort criterion for when the pilot is paused or pulled. The sponsor asked “what would make it a yes” and nothing measures the answer. | Dimension gap | High | Without success measures and an abort criterion the sponsor cannot make a defensible go/no-go or know when to stop. | Part A1; Part B #1,#2,#29 | Business rows: pilot success metrics with baselines and a written abort criterion; owned by Marcus Bell, approved by Dr. Anjali Rao. | 1 · Dimension gap |
| F3 | 16 | [Quality] Item 16 marks accessibility “N/A — backend service”, but Beacon drafts automated self-care replies to patients. ev-118 shows those replies at Grade 11. PCS-3 requires grade 8 or below and the patient’s chosen language. | Dimension gap; Contradiction | High | Patients could be sent self-care advice they cannot read, in a language they did not choose — a PCS-3 breach. | Part B #16; Part C E1; Part A2; Part A4 (PCS-3) | Review-stage Quality row: auto-reply readability ≤ grade 8 in all three languages, verified on a sample; owned by Victor Osei, approved by Dr. Helen Mathews. | 1 · Dimension gap |
| F4 | 25; None | [Operational] When Beacon sends a self-care reply and the patient writes back “it’s getting worse”, the reply lands in the general inbox, answered within 48 hours. No fast route back to a clinician exists. | Dimension gap; Contradiction | Critical | A deteriorating patient told to self-care has no quick route to a nurse — a patient-safety hazard. | Part C E4 (3 Dec); E8; Part B #25 | Operational row: defined escalation routing a worsening-symptom reply to a triage nurse within a set time; owned by Kavya Nair, approved by Priyanka Das. | 1 · Dimension gap |
| F5 | 1, 3; A5 | [Business] intent.md still limits the project to GP referrals, although portal messages and automated replies were added by an informal team-channel decision on 9 October. The sponsor has no approved statement of the patient-facing functionality now planned for release. | Stage gate; Contradiction | High | There is no formally approved intent for the automated patient-facing behaviour about to go live. | Part A5 (Intent); Part B #3; Part C E8 | Intent-stage Business row: update and business-approve intent.md for both channels, automated replies, clinical effects and phase scope. | 4 · Stage gate |
| F6 | 5; A2 | [Technical] Beacon connects to patient records and the portal through MedLink Systems. The October scope change was never re-architected (ADR-009 predates it) and the DPIA addendum is still missing, so the MedLink patient-message data flow has no reviewed failure path or privacy assessment; the signed DPA (item 5) covers neither. | Dimension gap; Evidence | High | A failure or data leak in the MedLink patient-message integration has no tested failover and no privacy assessment. | Part B #5; Part A2; Part C E8, E4 (2 Dec) | Spec/Review Technical row: reviewed MedLink integration failure path and DPIA coverage for the portal-message flow; owned by Imran Qureshi. | 1 · Dimension gap |
| F7 | 17; appendix | [Operational] ev-118 shows over-triage (routine classed as urgent) at 9.4%. With the night nurse queue already short-staffed, over-triage adds load to the same queue that must clear urgent cases in time — a safety-capacity issue, not just a nuisance. | Dimension gap; Evidence | Medium | Over-triage inflates the nurse queue the pilot is already too thinly staffed to clear, worsening urgent response times. | Part C E1 (over-triage); E4 (1 Dec) | Operational/Quality row: nurse-queue capacity sized against the evaluated over-triage and auto-route rates, not just the happy path. | 1 · Dimension gap |
| F8 | 18 | [Governance] R-17 (mixed-language under-triage, 6.8% vs 1.6% English, safety-critical) is recorded “accepted (N. Sharma, 5 Dec)”: Neha wrote “I’ve accepted it on behalf of delivery so we stay green for Thursday.” AIP-2 allows clinical risk to be accepted only by the CMO or CSO, in writing, with a review date. | Ownership; Contradiction | Critical | A safety-critical risk has been signed off by someone with no authority to accept it, so no clinician has judged it acceptable. | Part B #18; Part C E1 (R-17), E4 (5,7 Dec); Part A4 (AIP-2) | Governance row: R-17 accepted in writing by Dr. Anjali Rao or Dr. Helen Mathews with a review date, per AIP-2. | 2 · Ownership |
| F9 | 30; Appendix | [Governance] The appendix shows every stage gate — Intent, Spec, Plan, Build, Review — approved by one person, Neha Sharma, on one day (2 Dec); none by the role that should own it (CSO, DPO, CISO). #30 then calls the Go/No-Go a “formality” while clinical-risk acceptance, the CSO safety case, the DPIA and the fallback all remain open. | Stage gate; Ownership | Critical | A single self-interested sign-off on one day is not a gate; a board date must not waive mandatory patient-safety gates. | Part B #30, Appendix; Part C E4 (4–7 Dec); Part A4 | Role-appropriate approver at each gate and an explicit block/release rule; the 10 Dec meeting only confirms gates already passed. | 2 · Ownership |
| F10 | 4; A3 | [Technical] Item 4 “Architecture approved ✓ ADR-009 (September)”. ADR-009 is dated 21 Sep; portal messages and automated replies were added 9 Oct with no later review. The owner, Tobias Grant, is a contractor whose contract ends 18 December — four days after go-live — with no documented permanent technical custody. | Stage gate; Ownership | High | The integration carrying patient messages has no approved design, and its only owner leaves days after launch. | Part B #4; Part C E8; Part A3 | Spec-stage Technical row: architecture review for the added scope and a handover to a permanent owner (Imran Qureshi / Kavya Nair) before 18 Dec. | 2 · Ownership |
| F11 | 8, 9 | [Quality] Item 8 “Regression suite green” (CI #2291, 27 Nov) is owned by Jonas Weber, who left Kestrel on 16 October. Victor Osei notes the suite does not include the model evaluation set. Item 9 “Model validated” is also owned by Jonas Weber. | Ownership; Contradiction | High | A green regression tells the sponsor nothing about triage accuracy, and its named owner no longer works here. | Part B #8,#9; Part C E4 (27 Nov); Part A3 | Build-stage Quality row: regression owned by Victor Osei and including the model eval set; model-quality kept as a separate row. | 2 · Ownership |
| F12 | 19, 20 | [Operational] Item 20 “Alerts configured ✓ #beacon-alerts”. That channel has 14 members and is not on any on-call rota; Kavya Nair’s platform rota is paged only for infrastructure alerts, not model quality. | Ownership; Contradiction | High | A drift or safety alert would post into a chat nobody is on-call for, so no one would act. | Part B #19,#20; Part C E5 | Operational row: model-quality alerts to a named paged responder on a rota, with clinical escalation to Dr. Helen Mathews; owned by Kavya Nair. | 2 · Ownership |
| F13 | 10; Appendix | [AI control] Item 10 says the threshold is 0.80 per ev-118. The live config (a41f, 26 Nov) shows 0.72, lowered 25 Nov by Imran “to reduce nurse queue”, with the claim “eval numbers will be basically the same”. AIP-2 requires any threshold change affecting clinical output to be re-evaluated on Kestrel data and CSO-approved before use. | AI control; Contradiction | Critical | Lowering the threshold auto-routes more cases without a nurse, and 0.72 has never been measured on Kestrel data. | Part B #10, Appendix; Part C E3, E4 (26 Nov); Part A4 (AIP-2) | AI-01 row: metric, a number re-justified on Kestrel eval, owner Dr. Farah Siddiqui, CSO approval, change-control locking tuning. | 3 · AI control |
| F14 | 19 | [AI control] “Beacon Drift” compares category share and mean confidence to the CorvidBench supplier benchmark; no Kestrel baseline is loaded. There is no production measure of under-triage (the safety-critical metric); it is only findable by clinician sample review, and none is scheduled. | AI control; Evidence | Critical | The model could start under-triaging urgent patients and every dashboard would stay green. | Part B #19; Part C E5, E1 | AI-03 row: under-triage and auto-route rate by language segment vs the Kestrel ev-118 baseline, with a band, a clinician sample schedule, a paged responder and auto-routing paused on breach. | 3 · AI control |
| F15 | 17; A2 | [AI control] Item 17 “Human review for urgent cases ✓ 30-minute response”. At night 2 nurses across both sites also cover the ward phone; the urgent queue peaks at ~25 cases 7–10 pm, ~6 min each — ~75 min to clear, not 30. Beyond capacity, no routing safeguard defines the trigger, recipient, time bound or escalation for Emergency, low-confidence or worsening cases. | AI control; Contradiction | Critical | High-risk messages could sit in an ordinary queue or inbox with no enforced, tested routing path. | Part B #17; Part C E4 (1,3 Dec); Part A2 | AI-02 row: tested triggers and priority routing for emergency, below-threshold and worsening cases, under Priyanka Das, with a time bound and escalation on capacity failure. | 3 · AI control |
| F16 | 27 | [AI control] Item 27 “Vendor model-change process agreed”. The config pins no version — it uses the floating alias corvid-med-latest — and CTR-311 cl. 9.4 lets Corvid update “latest” with 14 days’ notice. Corvid’s 30 Nov notice moves the model to corvid-med-3.3 on 15 Dec, one day after go-live. AIP-2 requires re-evaluation on Kestrel data and CSO approval before use. | AI control; Contradiction | Critical | The triage model can silently change the day after launch with no Kestrel re-evaluation, directly against policy. | Part B #27; Part C E3, E8 (cl. 9.4), E4 (30 Nov); Part A4 (AIP-2) | Governance row: pin the model version; gate any Corvid change behind Kestrel re-evaluation and CSO approval. | 3 · AI control |
| F17 | A2 item 3; E3 | [AI control] The config enables auto_reply_categories: [routine, self_care], but the case describes automated replies only for Self-care. Routine patients could receive machine-drafted replies never scoped, planned or tested. | AI control; Contradiction | High | Patients with routine (not self-care) messages could get automated advice the programme never reviewed for safety. | Part C E3 (config); Part A2 (item 3) | Build/Review Quality row: constrain auto_reply_categories to the approved self-care scope and validate config against spec; owned by Victor Osei. | 3 · AI control |
| F18 | 9, 10 | [Quality] The internal evaluation ev-118 ran on 12 Nov on build 1.4.0 at threshold 0.80. The deployable build is 1.4.2 and the live threshold is 0.72. Items 9 and 10 still cite ev-118 as proof. | Stage gate; Evidence | Critical | The only Kestrel safety evidence does not describe the system that will actually go live. | Part B #9,#10; Part C E1 (footer), E3 | Build-stage Quality row: re-run the Kestrel evaluation on build 1.4.2 at 0.72 before go-live. | 4 · Stage gate |
| F19 | 12 | [Quality] Item 12 “Code review complete ✓ 87 of 87 PRs approved”. 12 PRs were approved by Imran Qureshi, who also wrote the prompts the coding agents used; ~70% of the code was agent-written. | Stage gate; Ownership | High | No independent human checked a meaningful share of agent-written code in a clinical system. | Part B #12; Part A5 (Review) | Review-stage row: an independent human approver who is not the prompt author for agent PRs; re-review the 12 self-approved. | 4 · Stage gate |
| F20 | 6 | [Governance] Item 6 “Feature plans complete ✓”. Plans exist for 9 of 11 features; “automated reply drafting” and “threshold tuning” have none and Imran calls them “small config features”. These are the patient-facing reply and the clinical threshold — the highest-risk behaviours. | Stage gate; Dimension gap | High | The two riskiest behaviours were built with no reviewed plan — exactly where later gaps appear. | Part B #6; Part A5 (Plan) | Plan-stage rows: approved plans, or a written waiver by a named owner, for automated-reply drafting and threshold tuning. | 4 · Stage gate |
| F21 | 15, 28; Appendix | [Governance] The appendix lets the network rollout (nine hospitals, 11 Jan) proceed automatically once the pilot Go/No-Go passes. Item 15’s load test is 3× pilot volume only; staffing, DPIA and the safety case are scoped to the two pilot sites — none of it proves the nine-site network or the clinical nurse queue. | Stage gate | Critical | Passing a two-site pilot would automatically authorise all nine hospitals with no separate evidence. | Part B #15,#28, Appendix | A distinct network-phase gate with its own criteria (network-scale load, all-site staffing, DPIA/safety-case coverage) before 11 Jan. | 4 · Stage gate |
| F22 | 7, 27; A5 | [Technical] Between the floating model alias, the un-planned threshold tuning and agent-written prompt changes, the exact model + prompt + build that will make live decisions cannot be tied to the evidence. Item 7 “code complete 1.4.2” does not fix the model/prompt/config actually running. | Stage gate; AI control | Critical | Evidence cannot be traced to the running clinical decision engine, so no result can be trusted for this release. | Part B #7,#27; Part C E3, E4 (30 Nov); Part A5 | Build/Deploy Technical row: version + hash attestation across build, prompt, model and supplier alias before release; owned by Imran Qureshi. | 4 · Stage gate |
| F23 | 9 | [Quality] Item 9 “Model validated (96% accuracy)” cites Corvid’s summary: 96.2% on CorvidBench-Triage — 48,000 US and UK primary-care messages. Kestrel patients write in English, Hindi or Marathi, often transliterated; Kestrel’s ev-118 shows 0.93 overall and 6.8% mixed-language under-triage. | Evidence; Contradiction | High | A US/UK accuracy figure tells the sponsor nothing about safety for Kestrel’s multilingual patients and overstates readiness. | Part B #9; Part C E2, E1; Part A1 | Quality row: validation on Kestrel’s own evaluation set, reported by language segment; owned by Dr. Farah Siddiqui. | 5 · Evidence / Contradiction |
| F24 | 14 | [Governance] Item 14 “DPIA approved ✓ DPIA v1, August”. Grace Liu notes DPIA v1 covers referral letters only; portal messages were added in October, so an addendum is needed before patient messages are processed. | Evidence; Contradiction | Critical | Processing patient-written messages without a DPIA addendum is a data-protection breach the DPO has already flagged. | Part B #14; Part C E4 (2 Dec); Part A3 | Review-stage Governance row: DPIA addendum for portal messages approved by Grace Liu before any patient message is processed. | 5 · Evidence / Contradiction |
| F25 | 21, 22 | [Governance] Item 21 logs only [message_id, category, confidence] — no rationale, model/prompt version, review outcome or sent advice. Item 22 sets retention to 365 days. RP-1 requires patient communications and the record of every care decision to be kept 8 years; #22’s owner is “Platform / Nursing (joint)”, not a person. | Evidence; Contradiction; Ownership | Critical | Kestrel could not reconstruct or defend a triage decision, and is deleting records seven years early, breaching RP-1. | Part B #21,#22; Part C E3; Part A4 (RP-1) | Rows requiring a full per-decision audit record and 8-year retention; owned by Kavya Nair, approved by Grace Liu. | 5 · Evidence / Contradiction |
| F26 | 23 | [Operational] Item 23 “Rollback rehearsed ✓ 1.4.2 → 1.3.9 in 4 minutes”. Only the application container was rehearsed. The model is hosted by Corvid via corvid-med-latest; the runbook does not cover the model version, the prompt version, or switching Beacon off so all messages go to nurses. | Evidence; Contradiction | High | If the model misbehaves after launch there is no rehearsed way to fall back to safe manual triage. | Part B #23; Part C E6 | Deploy-stage Operational row: rehearsed rollback covering model and prompt version plus a tested “all to nurses” manual-triage switch; owned by Kavya Nair. | 5 · Evidence / Contradiction |
| F27 | 26 | [Governance] Item 26 “Patient communication (AI disclosure) approved ✓ Draft with Communications”. The draft is with Legal and is English only. PCS-3 requires patients to be told when a message was drafted by an automated system, in their chosen language. | Evidence; Contradiction | High | Patients receiving an automated reply are not told it is automated, and not in Hindi or Marathi. | Part B #26; Part C E8; Part A4 (PCS-3) | Row: approved AI-disclosure wording in English, Hindi and Marathi; owned by Marcus Bell, approved by Grace Liu. | 5 · Evidence / Contradiction |
| F28 | 24 | [Operational] Item 24 “Triage nurses trained ✓ E-learning module assigned”. The 7 Dec learning report shows 11 of 29 pilot-site nurses (38%) have completed the module. | Evidence; Contradiction | Medium | Most nurses who must act on Beacon’s output at go-live have not been trained. | Part B #24; Part C E8 | Deploy-stage Operational row: at least the agreed proportion of pilot-site nurses trained, with completion evidence; owned by Kavya Nair, approved by Priyanka Das. | 5 · Evidence / Contradiction |
| F29 | 29 | [Governance] Item 29 “Board communication” and E4 (4 Dec, “we cannot slip”) use the board’s announcement of the 14 Dec pilot as a reason not to move the date. A communication is not a safety authority. | Governance; Evidence | High | Schedule pressure from a board announcement is being used to override mandatory clinical and policy gates. | Part B #29; Part C E4 (4 Dec); Part A4 | Business/Governance row: the date may move; no board announcement waives a mandatory clinical or policy control; owned by Marcus Bell. | 1 · Dimension gap |
| F30 | 7, 8, 13, 15 | [Evidence] Genuine positive evidence exists and must not be marked universally failed: build 1.4.2 is merged, regression CI #2291 is green, penetration test PT-2026-77’s critical finding is fixed and signed-off on retest (30 Nov), and pilot-volume load LT-1.4.2 passed. These are narrowly Met. | Evidence | Medium | Inaccurate pessimism is as misleading as unchecked green ticks; the sponsor must see what truly is ready. | Part B #7,#8,#13,#15; Part C E4 (27 Nov) | Keep narrowly scoped Met rows (pen test; pilot load), separating model performance and other unproven controls from them. | 5 · Evidence / Contradiction |

# Part 3 · Governance frame (M2)

## 3a · Who owns each dimension?

Exactly one Accountable person per dimension, by name, from Part A3. Each passes the Saturday question: if this fails on go-live weekend, this is the person whose phone rings and who can say “I checked, here is the evidence.”

| Dimension | Accountable (one named person) | Responsible | Consulted | Informed | Why this person (one sentence) |
| --- | --- | --- | --- | --- | --- |
| Business | Marcus Bell | Neha Sharma | Dr. Anjali Rao; Priyanka Das; Sunil Bhat | Owen Fletcher | Owns the business case, scope and patient-facing launch outcomes. |
| Technical | Imran Qureshi | Tobias Grant (to 18 Dec); Kavya Nair | Rahul Menon; Dr. Farah Siddiqui | Neha Sharma | Owns code, AI-agent changes and release integrity; the contractor is time-limited. |
| Quality | Victor Osei | Dr. Farah Siddiqui | Dr. Helen Mathews; Priyanka Das | Dr. Anjali Rao | Owns the independent test strategy and exact-build validation evidence. |
| Governance | Dr. Helen Mathews | Owen Fletcher (AIP-2/risk); Grace Liu (DPIA); Rahul Menon (security) | Dr. Anjali Rao; Dr. Farah Siddiqui | Neha Sharma | CSS-1 requires the Kestrel CSO to own and sign the clinical safety case; the dominant governance risks here are clinical, and AIP-2 allows clinical-risk acceptance only by CSO or CMO. |
| Operational | Kavya Nair | Priyanka Das; Sunil Bhat | Dr. Helen Mathews; Imran Qureshi | Dr. Anjali Rao | Owns monitoring, alerting and on-call, integrating the clinical response workflow. |

The three AI-control rows (AI-01/02/03) name the control’s metric owner, per the AI Governance Policy Design rubric; the five dimension Accountables above are unchanged.

## 3b · Where is each dimension checked? (stage-gate map)

Each cell names who approves crossing the gate and the artefact they look at. All six stages are used and four dimensions have gates at more than one stage.

| Dimension | Intent | Spec | Plan | Build | Review | Deploy |
| --- | --- | --- | --- | --- | --- | --- |
| Business | Appr: A. Rao · updated intent + pilot-site minutes |  | Appr: A. Rao · success metrics + abort plan |  |  | Appr: A. Rao · multilingual disclosure; separate pilot & network decision records |
| Technical |  | Appr: K. Nair · reassessed ADR + handover | Appr: Dr. H. Mathews · auto-reply & threshold-tuning plans | Appr: V. Osei · build manifest + version/hash attestation | Appr: V. Osei · 12 independent PR re-reviews; PT retest | Appr: K. Nair · pinned model + full rollback test |
| Quality |  |  |  | Appr: Dr. H. Mathews · exact-build Kestrel eval | Appr: Dr. H. Mathews · multilingual UAT + segment review |  |
| Governance |  | Appr: O. Fletcher · AIP-2 change-control spec + pinned model |  |  | Appr: A. Rao / G. Liu · CSS-1 safety case; DPIA addendum; signed clinical-risk register | Appr: G. Liu · 8-year retention / audit proof |
| Operational |  | Appr: Dr. H. Mathews · nurse-trigger & escalation spec | Appr: P. Das · queue-capacity calc |  |  | Appr: P. Das / Dr. H. Mathews · trained rota, pager drill, manual-mode failover |

## 3c · What is the 10 December Go/No-Go for now?

The 10 December pilot Go/No-Go only confirms that independently approved stage gates and clinical evidence are already recorded, then records Dr. Anjali Rao’s pilot decision; a separate 11 January network gate requires pilot-outcome and nine-site readiness evidence.

## 3d · Phase gates (pilot vs network)

| Phase gate | Timing | Mandatory entry evidence | Approver / rule |
| --- | --- | --- | --- |
| Pilot | 10 Dec decision; 14 Dec go-live | Kestrel CSO clinical safety case; exact-build (1.4.2 / 0.72) Kestrel eval; safe multilingual triage with a staffed nurse queue; signed DPIA addendum; 8-year audit records; live clinical drift monitor; model + prompt rollback and manual-triage failover; approved multilingual AI disclosure. | Dr. Anjali Rao decides; Dr. Helen Mathews approves all clinical-risk controls. NO GO if any mandatory clinical or policy control is missing. |
| Network | Independent decision before 11 Jan | Two-site pilot outcomes and adverse events; current approved model; all nine sites capacity-tested, staffed and trained; audits, fallback, privacy and local safety-case coverage verified. | Dr. Anjali Rao with Dr. Helen Mathews clinical sign-off; pilot approval is not automatic network authorisation. |

# Part 4 · Release-Readiness Checklist v1 (M3) — scored work product

## 4a · Header block

| Field | Your entry |
| --- | --- |
| Product / release | Beacon 1.4.2 — AI-assisted patient triage (urgency categorisation, automatic routing, automated self-care replies), Kestrel Health Network. |
| Phases gated | Pilot: Riverside + Hillcrest, 14 Dec 2026 · Network: all nine hospitals, 11 Jan 2027. Each row shows the phase it gates. |
| Checklist version | v1 · candidate 290222 · evidence snapshot 8 Dec 2026 |
| Governance structure | Enforced control · evidence artefact · durable log · named approver; phase-specific stage gates; no clinical-risk waiver by delivery. |
| Accountable owners by dimension | Business: Marcus Bell · Technical: Imran Qureshi · Quality: Victor Osei · Governance: Dr. Helen Mathews · Operational: Kavya Nair. |
| Purpose of the 10 Dec Go/No-Go | Confirms independently approved, evidenced gates and records Dr. Anjali Rao’s pilot decision; network expansion needs a separate 11 Jan gate. |

## 4b · Criteria

AI-control rows first (AI-01 confidence threshold · AI-02 human-in-the-loop trigger · AI-03 model drift monitor), each stating every required field, then one row per finding. Status is honest as of 8 Dec 2026. Met = light green · Unknown = light amber · Not met = plain.

| ID | Stage | Phase | Dimension | Criterion (a checkable, enforced question) | Evidence required | Where logged | Accountable owner (named) | Approver | Status as of 8 Dec + basis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AI-01 | Build | Both | Governance | Confidence threshold — is the auto-route decision governed by a single CSO-approved confidence-score threshold (metric), fixed to a value validated on Kestrel’s ev-118 data (origin: only 0.80 on build 1.4.0 is validated, so the live 0.72 is blocked until re-evaluated on 1.4.2), owned by Dr. Farah Siddiqui, with every below-threshold case sent to a nurse and any retune frozen until re-evaluation and CSO sign-off? | Kestrel eval report naming build + threshold; threshold rationale; change-control record carrying CSO approval | Repo config; eval register; AIP-2 change log | Dr. Farah Siddiqui | Dr. Helen Mathews | Not met — live config is 0.72 (E3), lowered 25 Nov with no re-eval or CSO approval; only 0.80 on 1.4.0 is validated (F13; AIP-2). |
| AI-02 | Spec | Both | Operational | Human-in-the-loop trigger — are all Emergency/Urgent cases, every below-threshold or low-confidence output, and every worsening-symptom reply (conditions) routed to the prioritised triage-nurse queue under Priyanka Das (role) within a 30-minute urgent-response target enforced by a timer with defined escalation if breached (time bound), and is that target demonstrably met by the staffed night rota? | Written trigger rules; nurse rota with capacity maths vs the 7–10 pm peak; timed route tests; escalation runbook | spec.md; nursing rota; contact-centre runbook | Priyanka Das | Dr. Helen Mathews | Not met — 2 night nurses also cover ward phones; ~25-case peak ≈ 75 min vs the 30-min target; worsening replies sit 48 h; emergency/low-confidence routing untested (F15, F12, F4). |
| AI-03 | Deploy | Both | Operational | Model drift monitor — are under-triage (overall and mixed-language), auto-route rate and category mix (measure) tracked against the Kestrel ev-118 baseline (2.1% overall, 6.8% mixed-language, 1.6% English, 69% auto-route at 0.80) within a CSO-ratified band of ±3 points on overall under-triage and auto-route rate — mixed-language under-triage not above English parity by more than ~1 point — paged to Kavya Nair with clinical escalation to Dr. Helen Mathews, auto-pausing auto-routing into manual triage and opening an incident on breach? | Dashboard with the Kestrel baseline loaded; sampling protocol; paged-alert + pause drill; written breach action | Monitoring system; incident runbook | Kavya Nair | Dr. Helen Mathews | Not met — “Beacon Drift” uses the CorvidBench baseline, has no under-triage measure, and alerts post to an unpaged channel (F14, F12). The ±3-point band and all Part 6 figures are exploratory proposals pending CSO ratification, not deployment thresholds — no release until clinically approved. |
| B-01 | Intent | Both | Business | Are the August business case and the September executive pilot-site selection recorded (without claiming the October portal/reply scope was approved)? | Board paper; executive minutes | Programme decision register | Marcus Bell | Dr. Anjali Rao | Met — Aug business case and Sep two-site decision exist (items 1,2); the October scope change is separately Not met (B-02). |
| B-02 | Intent | Pilot | Business | Does intent.md state the current built scope, including the portal messages and automated replies added on 9 October? | Updated intent.md showing the date and the added scope | Repo (intent.md) | Marcus Bell | Neha Sharma | Not met — intent.md still covers referral letters only; portal messages/auto-replies were added via the team channel and never written in (A5, F5). |
| B-03 | Plan | Pilot | Business | Are pilot success metrics (under-triage by language, nurse response time, auto-route rate, communication quality) defined with baselines and reporting cadence, and is there an abort criterion stating when the pilot is paused or pulled? | Metric definitions with baselines; stop rules; sponsor decision form | Programme decision register | Marcus Bell | Dr. Anjali Rao | Not met — board date is published but no measured success target or abort criterion exists (F2; items 1,29, E1). |
| B-04 | Deploy | Pilot | Business | Is the patient AI-disclosure wording approved and available in English, Hindi and Marathi before any automated reply is sent? | Approved disclosure text in three languages; sign-off | Communications register | Marcus Bell | Grace Liu | Not met — English-only draft with Legal (E8; PCS-3) (F27). |
| B-05 | Deploy | Network | Business | Does network expansion require a separate sponsor decision based on pilot outcomes, safety incidents and nine-site readiness, rather than proceeding automatically? | Pilot outcome report; signed 11 Jan network go/no-go | Programme decision register | Marcus Bell | Dr. Anjali Rao | Not met — the appendix assumes automatic expansion once the pilot passes (F21; item 28). |
| T-01 | Spec | Pilot | Technical | Has the integration architecture been reviewed and approved for the added scope (portal messages + automated replies) by a permanent named owner, with handover before Tobias Grant leaves on 18 Dec? | Post-9-Oct ADR; signed design/security review; architecture handover note | ADR register; spec.md | Imran Qureshi | Kavya Nair | Not met — ADR-009 dates 21 Sep; no later review; the contractor leaves 18 Dec with no handover (F10, E8). |
| T-02 | Build | Both | Technical | Is the pilot code the exact evaluated build with the config (model alias, threshold) matching what was validated? | Build/commit id; config diff vs the evaluated version | Pipeline logs; repo | Imran Qureshi | Victor Osei | Not met — eval ran on 1.4.0 at 0.80; deployable build is 1.4.2 and config a41f sets 0.72 and a floating alias (F18, E3). |
| T-03 | Review | Both | Technical | Do all 12 agent-prompt-originated PRs approved by Imran have independent human reviewer approval, and have they been re-reviewed? | PR approval list; re-review sign-offs comparing author vs approver | PR history | Imran Qureshi | Victor Osei | Not met — 12 PRs approved by Imran, who wrote the agent prompts; ~70% of code agent-written (F19, A5). |
| T-04 | Deploy | Both | Technical | Has full fallback been rehearsed for application, prompt and model version, plus switching automated routing/replies off into manual nurse triage? | Timed rehearsal with all components/versions and shift staffing verified | Runbook §5; pipeline logs | Imran Qureshi | Kavya Nair | Not met — only the app container (1.4.2 → 1.3.9) was rehearsed; the runbook omits model/prompt version and manual triage (F26, E6). |
| T-05 | Review | Pilot | Technical | Is penetration test PT-2026-77’s critical finding fixed and independently retested, with scope tied to the pilot release? | Signed PT-2026-77; 30 Nov retest; scope mapping | Security register | Imran Qureshi | Rahul Menon | Met — critical fixed, retest passed 30 Nov, signed R. Menon (item 13); future scope not implied (F30). |
| T-06 | Review | Pilot | Technical | Has a load test passed on the release build at the expected pilot volume? | Load-test report naming the build | Performance register | Imran Qureshi | Kavya Nair | Met (pilot only) — LT-1.4.2, 1 Dec: p95 1.8 s at 3× pilot volume (item 15); no network-scale result implied (F30). |
| T-07 | Build | Both | Technical | Is the exact model + prompt + build attested by version/hash so evidence ties to the running decision engine, with a pinned model identifier (not corvid-med-latest) and the 15 Dec Corvid upgrade prevented until local re-evaluation and CSO sign-off? | Immutable model/config manifest with hashes; supplier version; prompt-change records; change-control proof | Configuration repository; AIP-2 / supplier-change register | Imran Qureshi | Dr. Helen Mathews | Not met — floating alias, un-planned tuning and agent prompt changes make the live model/prompt unknowable; 3.3 upgrade due 15 Dec (F22, F16, E3, E4). |
| T-08 | Spec | Both | Technical | Does the MedLink patient-record/portal integration have a reviewed failure path and DPIA coverage for the portal-message flow added in October? | MedLink integration failure test; DPIA addendum covering the flow | Architecture register; DPIA register | Imran Qureshi | Grace Liu | Not met — the Oct scope was never re-architected and the DPIA addendum is missing; the signed DPA (item 5) covers neither (F6, E8, E4). |
| T-09 | Review | Network | Technical | Has load/capacity testing been repeated for nine-site concurrency and the third-party model/API dependencies before 11 Jan? | Nine-site volume model; test run; SLO; supplier evidence | Performance register | Imran Qureshi | Kavya Nair | Unknown — only the 3× pilot-volume result LT-1.4.2 exists; no nine-site test (F21; item 15). |
| Q-01 | Build | Pilot | Quality | Has Kestrel’s own evaluation been re-run on the deployable build (1.4.2) at the live threshold (0.72), reporting accuracy and under-triage by language segment? | Signed eval report with build/model/config hashes and urgency metrics | Kestrel eval register | Victor Osei | Dr. Helen Mathews | Not met — the latest Kestrel eval (ev-118) is build 1.4.0 at 0.80 (F18, E1, E3). |
| Q-02 | Build | Both | Quality | Is accuracy validated on Kestrel’s multilingual evaluation set (not a supplier US/UK benchmark), with mixed-language under-triage within an agreed clinical tolerance? | Kestrel eval by language segment; written clinical acceptance tolerance | Kestrel eval register | Victor Osei | Dr. Helen Mathews | Not met — item 9’s “96%” is Corvid’s CorvidBench (US/UK); Kestrel ev-118 shows 6.8% mixed-language under-triage (F23). Tolerance ≤ 2% proposed in Part 6. |
| Q-03 | Review | Pilot | Quality | Do automated self-care replies meet PCS-3 (grade ≤ 8, patient’s chosen language), disclose machine drafting, and exclude any unapproved routine auto-replies? | Clinician-reviewed scripts; readability/language results; release config diff | Content register; repo config | Victor Osei | Dr. Helen Mathews | Not met — item 16 marks accessibility N/A “backend”; E1 shows Grade 11, English only; config enables the routine category (F3, F17; PCS-3). |
| Q-04 | Build | Pilot | Quality | Does the suite that gates the build include the model evaluation set, and is it owned by a current employee? | CI run including the eval set; named owner | CI register | Victor Osei | Imran Qureshi | Not met — CI #2291 excludes the model eval set and is attributed to Jonas Weber, who left 16 Oct (F11, E4). |
| Q-05 | Review | Pilot | Quality | Have nurse-led end-to-end UAT cases demonstrated safe handling of emergencies, urgent referrals, below-threshold cases and symptomatic follow-up replies at both sites, on the exact release configuration? | Signed nurse UAT scripts and results for both pilot sites | UAT register; clinical operations SOP | Victor Osei | Priyanka Das | Unknown — no completed nurse-led UAT evidence in the case (A5, B17, E1–E8). |
| G-01 | Review | Pilot | Governance | Is a Kestrel-specific CSS-1 safety case and hazard log — covering auto-replies, mixed-language triage, queue capacity and model change — signed by the Kestrel CSO (Corvid’s log an input only)? | Kestrel safety case + hazard log signed by the CSO | Clinical safety register | Dr. Helen Mathews | Dr. Anjali Rao | Not met — item 11 rests on Corvid’s Hazard log v2; the CSO has not been asked to review (F1; CSS-1, E7). |
| G-02 | Review | Pilot | Governance | Has Grace Liu approved a DPIA addendum covering patient-portal messages and automated disclosures before any patient message is processed? | Signed DPIA addendum; processing-flow assessment | DPIA register | Dr. Helen Mathews | Grace Liu | Not met — DPIA v1 (Aug) covers referral letters only; addendum flagged needed 2 Dec (F24, E4). |
| G-03 | Spec | Both | Governance | Does any change to the model, prompt or threshold affecting clinical output require fresh Kestrel evaluation and CSO sign-off before use, with the model version pinned? | AIP-2 change register; immutable manifest; CI block test | AIP-2 change log; platform policy gate | Dr. Helen Mathews | Owen Fletcher | Not met — config uses floating “corvid-med-latest”; 0.72 tuning and the 3.3 upgrade bypass approval (F16, F13; AIP-2). |
| G-04 | Review | Both | Governance | Can R-17 or any clinical risk be accepted only in writing by the CMO or CSO with a review date, per AIP-2? | Signed clinical risk acceptance with review date; updated R-17 | Enterprise risk register | Dr. Helen Mathews | Dr. Anjali Rao | Not met — R-17 recorded “accepted (N. Sharma, 5 Dec)”; the delivery lead cannot accept clinical risk (F8; AIP-2, E4). |
| G-05 | Deploy | Both | Governance | Does every triage decision write an 8-year audit record (message id, category, confidence, rationale, model + prompt version, review outcome, sent advice), per RP-1? | Sample audit record with all fields; verified 8-year retention config | Audit store; records register | Dr. Helen Mathews | Grace Liu | Not met — log_fields = [message_id, category, confidence]; retention 365 days (F25; RP-1, E3). |
| G-06 | Plan | Pilot | Governance | Do the two highest-risk features — automated reply drafting and threshold tuning — have approved plans or a written waiver by a named owner? | Plan documents or a written waiver with clinical impact assessment | Repo (beacon/plans/) | Dr. Helen Mathews | Owen Fletcher | Not met — no plans exist; Imran calls them “small config features” (F20, A5). |
| G-07 | Review | Pilot | Governance | Were evidence-based stage gates independently approved by the appropriate clinical, QA, privacy and security authorities before the 10 Dec sponsor meeting? | Gate register with dated independent sign-offs and links | Release gate register | Dr. Helen Mathews | Dr. Anjali Rao | Not met — Neha Sharma signed all gates on 2 Dec despite open safety issues (F9, Appendix). |
| O-01 | Deploy | Pilot | Operational | Are clinical/model-quality alerts paged to named on-call responders — Kavya Nair with clinical escalation to Dr. Helen Mathews — with receipt and action rehearsed? | Pager rotation; acknowledgement drill; escalation chain; incident action | Grafana alert log; on-call schedule | Kavya Nair | Dr. Helen Mathews | Not met — alerts post to a 14-member chat channel with no model-quality rota (F12, E5). |
| O-02 | Deploy | Pilot | Operational | Does the contact centre have approved deterioration call scripts and an urgent transfer route rather than 48-hour inbox processing? | Scripts; call simulation; routing config; training sign-offs | Contact-centre SOP; escalation register | Kavya Nair | Sunil Bhat | Not met — only a release-notes email; no scripts or escalation (F4, E8, E4). |
| O-03 | Deploy | Pilot | Operational | Have the pilot triage nurses achieved documented training competency and safe on-shift assignment (or an explicit CSO-approved coverage plan)? | LMS completion and competency acknowledgement; staffing rota | Learning system; pilot rota | Kavya Nair | Priyanka Das | Not met — 11/29 (38%) complete on 7 Dec (F28, E8). |
| O-04 | Deploy | Pilot | Operational | Is nurse-queue capacity sized for the evaluated routing load, including the 9.4% over-triage rate, the 7–10 pm peak and the night rota? | Roster; queue-load simulation vs ev-118 rates; escalation sign-off | Pilot operations readiness register | Kavya Nair | Priyanka Das | Not met — 2 night nurses also cover ward phones; ~75-min clearance; over-triage adds load (F15, F7; E4, E1). |
| O-05 | Deploy | Pilot | Operational | Can signed deployment records confirm pilot configuration/version, an operational kill switch, and staff capacity for immediate manual triage? | Deploy manifest; manual-mode failover rehearsal; staffing confirmation | Deployment logs; runbook §5 | Kavya Nair | Dr. Helen Mathews | Not met — container-only rollback; no manual-triage mode test (F26, E6). |
| O-06 | Deploy | Network | Operational | Are all nine sites independently trained, staffed, monitored and equipped for manual fallback before 11 Jan, based on pilot outcomes? | Site readiness attestations; nine-site drill evidence; pilot safety review | Network rollout gate register | Kavya Nair | Dr. Anjali Rao | Unknown — only two pilot sites planned; no nine-site evidence (F21, item 28). |

# Part 5 · Readiness statement to the sponsor (M4)

Half a page to Dr. Anjali Rao — written so it could be forwarded to the regulator unchanged.

| Heading | Statement |
| --- | --- |
| To | Dr. Anjali Rao, Chief Medical Officer and Programme Sponsor |
| Decision for 14 December | No-Go as it stands; Go only when the conditions below are met and evidenced. The straight answer is that Beacon is not yet safe to auto-route or auto-reply to patients. |
| What is ready | The penetration test (PT-2026-77) is fixed and independently retested (30 Nov); pilot-volume load passed (p95 1.8 s at 3× pilot volume); the business case and the two pilot sites are approved. |
| What is not ready (blockers) | No Kestrel clinical safety case (CSS-1); R-17 accepted without CMO/CSO authority (AIP-2); the live 0.72 threshold is unvalidated and the model alias changes on 15 Dec (AIP-2); no DPIA addendum for portal messages; no production under-triage/drift monitor and alerts are unpaged; the audit record and 365-day retention breach RP-1; auto-replies are Grade 11 and English-only (PCS-3); worsening-symptom replies wait 48 hours; nurse training is 38%; the night human-in-the-loop clears in ~75 minutes, not 30. |
| What would make it a yes (each specific, owned, checkable) | 1) CSO-signed Kestrel safety case + hazard log (Mathews). 2) R-17 accepted in writing by the CMO or CSO with a review date (Rao/Mathews). 3) Re-evaluation on build 1.4.2 at a pinned model with a CSO-approved threshold (Siddiqui/Mathews). 4) DPIA addendum for portal messages (Liu). 5) Live drift monitor on the Kestrel baseline, paged on-call, with clinician sampling (Nair/Mathews). 6) Full per-decision audit record and 8-year retention (Nair/Liu). 7) PCS-3-compliant multilingual replies and disclosure (Osei/Mathews). 8) A staffed night rota that meets the urgent-response target with tested escalation (Das). 9) Agreed nurse-training completion. |
| Before the 11 January network rollout | A separate network gate — all-nine-site staffing and training, a network-scale load test, and DPIA and clinical-safety coverage for every hospital — decided by the sponsor with CSO clinical sign-off, not automatically authorised by the pilot. |
| Recommendation | Hold the 14 December pilot. The board announcement is a schedule, not a safety authority. Re-gate once the clinical-safety, policy and monitoring conditions above are met and the evidence is logged; this statement is written so it can be forwarded to the regulator unchanged. |

# Part 6 · Assumptions

Figures the case did not state, proposed here and pending CSO ratification.

| # | What I assumed | Why I needed to assume it |
| --- | --- | --- |
| A1 | Until a Kestrel re-evaluation on build 1.4.2 fixes a value, the auto-route threshold is held at the last CSO-validated figure (0.80 on ev-118) and 0.72 is blocked. | The case gives no validated figure for build 1.4.2 / 0.72, and AIP-2 forbids using an unvalidated threshold. |
| A2 | AI-03 drift band: ±3 points on overall under-triage and auto-route rate vs the ev-118 baseline, with mixed-language under-triage not permitted above English parity by more than ~1 point — subject to CSO ratification. | E5 states no numeric band exists in the case; a monitor needs a concrete band to alert against. |
| A3 | Q-02 clinical tolerance: mixed-language under-triage must reach near-parity with English (target ≤ ~2%) before release. | ev-118 shows 6.8% mixed-language vs 1.6% English; the case sets no acceptance level, so one is proposed for CSO sign-off. |
| A4 | AI-02: the urgent-response target is taken as the stated 30 minutes, treated as achievable only with a staffed night rota, and an escalation fires if the timer is breached. | Item 17 claims 30 minutes; E4 (1 Dec) shows ~75 minutes, so the target is retained as a goal conditional on staffing. |
| A5 | O-03: the nurse-training completion gate is assumed at 100% of rostered pilot-site nurses, or an explicit CSO-approved coverage plan, before pilot. | The case gives 38% completion but no required threshold; a gate value is needed to judge readiness. |

# Before you submit

| Check | Done? |
| --- | --- |
| Part 1: cover block complete | ☑ |
| Part 2: 15+ findings covering all five dimensions; all 30 v0.9 items referenced; F0 example row deleted | ☑ |
| Part 3: one named Accountable per dimension (no teams, no TBD); stage-gate map with approver + artefact; phase gates set | ☑ |
| Part 4: AI-01/02/03 as separate full rows (threshold, HITL trigger with time bound, drift monitor with band); all six stages; every row has evidence, log, owner, approver, phase and honest status | ☑ |
| Part 4: statuses match the evidence — Not met / Unknown appear where the evidence says so; genuine Met rows kept | ☑ |
| Part 5: readiness statement written (what is ready, what is not, what makes it a yes, and the network condition) | ☑ |
| Part 6: assumptions recorded for every proposed figure | ☑ |